## Tasks
Sr.No	Assignee	Assigned to	Date	Task Group1	Task	History	Steps/Requirement	Status	Remarks	Priority
1	Self	PK	1. Oct. 2019	Self-Assigned	Read Zerodha site	11 Oct 2019 – / Gone through first 3 modules		In progress		3
2	BV	PK	1. Oct. 2019	Code-Review-Release-Mgmt	Code Review / Release management	27-Nov-2019- / As earlier discussed with Ajay and Brijesh sir, few users have been added in GitLab and access mail triggered to them. / 06-Nov-2019- / * As discussed with B.V. currently our few features (Login , Commodity and ) is being developed on priority, so we can hold our GIT movement post completion of these functionality. / 05-Nov-2019- / * SVN Branches for latest version of code deployed in production is shared from Birender. Now task is to configure new code in GitLab as base. / 04-Nov-2019- / * Shared the current status for code review to Brijesh and Ajay sir. Main roadblock observed as the identification of base code, upon which new changes can be tracked . / 31-Oct-2019- / * Got access on VSS. / * Had one discussion with Brijesh, Annapurna, Saroj for current flow to maintain code in Working Directory folder, VSS and local system. / * Few application are on VSS and Few are on SVN. / 22-Oct-2019 - / Explored code coverage tools / 1. Cobertura / 2. PMD / 3. Jacoco / PMD can be further used for our purpose. / 18-Oct-2019 - / New user premendra.kumar created. / Need to explore for code review process. / 17 Oct 2019 - / * Access to SVN Code / * Code configured in eclipse / * Initial discussion done with assignee for points to be covered in code review	18-oct-2019 / * Access to svn / * Set up for workflow for code commit and approval before deployment in test/uat environment / 1. Separate ids for each developers / 2. pull request architecture for merge code in main branch	On hold	27-Nov-2019- / As earlier discussed with Ajay and Brijesh sir, few users have been added in GitLab and access mail triggered to them. / Blockers:- / 1. Latest code running in prod not available. / 2. Training to use git is not being entertained / 3. Waiting for stable version of code.	1
3	BV	PK	4. Oct. 2019	Code-Review-Release-Mgmt	SVN to GIT with history	27-Nov-2019- / As earlier discussed with Ajay and Brijesh sir, few users have been added in GitLab and access mail triggered to them. / 20-Nov-2019- / 18 Oct 2019 - / User premendra.kumar created / Need to explore git-svn / 17 Oct 2019 - / * Access to GitLab code / * Gone through search engine for possibility for SVN to git with history	SVN / Git / Git-svn	On hold	22 Oct 2019 - / As discussed with Brajesh sir, we can / 1. move current code of production to Git / 2. Will make all ids on SVN as read only to stop further commits, now all commits should be done in GIT only / 3. Maintain production code on master. / 4. Developers should work on their branch only, pull request before merge code in master. Tag to be created before every merge. / 5. Testing should be done on tag code only. / 6. Post test sign-off tag code will move to further environment.	1
4	Self	PK	16. Oct. 2019	Self-Assigned	Read svn-book.pdf			Open		5
5	Self	PK	10/18/19	Self-Assigned	Read for ReactJS	07-Nov-2019- / Reading reactjs from w3schools and trying to clear concepts.	* https://reactjs.org/tutorial/tutorial.html	In progress		5
6	BV	PK	22. Oct. 2019	Code-Review-Release-Mgmt	Prepare one presentation for / 1. Git push/pull , checkin, checkout / 2. Benefits for GIT over SVN	30-Oct-2019- / KT Taken from manoj for NoticeAPI. Code uploaded in GIT. Code configured and run in local eclipse as well as through provided batch file. / 24-Oct-2019- / * Overview ppt created / * Initial discussion done with Team @3PM today / 23-Oct-2019 - / KT Preparation in progress.		Done	KT Preparation in progress.	1
7	BV	PK	22. Oct. 2019	Shubh-Web-BOR-Jar	Configure stub code of WebServiceBOR code and change IP	20-Nov-2019- / Updated jar tested and shared to Anmol and Birender. New WebServiceBOR.jar / 28-Oct-2019- / Code generated from given WSDL file and created jar shared to Birender to get tested with Anmol. / 22-Oct-2019- / Decompiled code and changed given IP. / Further testing on hold due to port connectivity issue with new server		Done	25-Oct-2019- / *New wsdl file has been shared from Birender . Need to create new stub project with shared WSDL file. / 22-Oct-2019- / * New jar has been created. / * Further testing on hold due to port connectivity issue with new server	2
8	DJ	PK	23. Oct. 2019	Code-Review-Release-Mgmt	Migration of Code / 1. Web / 2. PIB / 3. Mobile		1. KT For Git , comparison with SVN to be given to all team members. / 2. Put all source code on git. (Need a systematic plan to do so) / 3.	In progress	KT Preparation in progress.	2
9	DJ	PK	23. Oct. 2019	Code-Review-Release-Mgmt	PIB Client tr code – move initial code to git	source code shared from Mausami/Deepak has been put on git in as-is state. Builds are being make properly, as checked from Deepak system.		Done
10	DJ	PK	24. Oct. 2019	Code-Review-Release-Mgmt	PIB Client tr code – Reorganize code for some standard folder structure.	04-Nov-2019- / Code of client tr shared from Mousumi and VSS has some differences. Asked Mousumi to confirm and shared final code, which could be used for base code. / 25-Oct-2019- / * Reorganizing of code in said folder structure done. / * Source/store, Source/images, Source/logs folder removed from GIT as these folders will create on time of running Jar. So no need to keep them in version control. / 24-Oct-2019 / * Separate branch named “mavenized-branch” created. / * Reorganising of code in said folder structure in progress.	1. make separate branch / 2. Reorganise code and other files among src, bin, classes, build, logs folders / 3. Modify batch file to run and make same build in new folder structure. / 4. Get the code tested. If ok, make tag and separate stable branch / 5. Translate modified batch file to equivalent maven file.	In progress	25-Oct-2019- / Restructured code has been commited on GiLab and build step process shared with Deepak and Brijesh. / Testing in progress / 24-Oct-2019- / As checked, the output directory generated with only .class files and it excludes other .gif and .dll extension files if code gets compiled from ant post deleting old output directory. This is roadblock to make build from ant file.	2
11	BV	PK	24. Oct. 2019	Notic-KRA-KUA	Take KT From Manoj for an API provided from Exchange		Take KT from Manoj before 31st Oct	Done	25-Oct-2019- / Task in progress as Manoj is on leave today. / 24-Oct-2019- / Task to be start from tomorrow.	1
12	BV	PK	4. Nov. 2019	Notic-KRA-KUA	Live the NoticAPI code to prod and check results	05-Nov-2019- / As per discussion with B.V. Code on main terminqal server to be run in evening and check the results.		Done		1
13	BV	PK	5. Nov. 2019	Shubh-Web-Login-TR	Test for “Forgot Password (Pre Login)” APIs from Postman	06-Nov-2019- / * IP Whitelisted from Basant sir side. OTP also receiving with help of Rohit sir. However mail is not triggering. Rohit sir checking the issue post which I will work / Accordingly. / * As tested, now OTP is coming on mobile as well as mail. / 05-Nov-2019- / PublicKey3 has been generated from code and now I need to hit APIs for “Forgot password(Pre Login)”. / Roadblock – IP of my system needs to be whitelisted . Ask Basant sir to do the same.		Done	06-Nov-2019- / * IP Whitelisted from Basant sir side. OTP also receiving with help of Rohit sir. However mail is not triggering. Rohit sir checking the issue post which I will work / Accordingly. / * As tested, now OTP is coming on mobile as well as mail.	1
14	Self	PK	5. Nov. 2019	Self-Assigned	Mavenize the given code to generate public key3 project with spring boot rest and jackson	06-Nov-2019- / Tried to write equivalent code . The libraries are manually pointed out from a remote server folder @ 49 server. This manual configuration of jar configuration with maven custom repository/artifactory configuration.		Done	06-Nov-2019- / Tried to write equivalent code . The libraries are manually pointed out from a remote server folder @ 49 server. This manual configuration of jar configuration with maven custom repository/artifactory configuration.
15	Self	PK	5. Nov. 2019	Self-Assigned	Read Nest REST API Documentation “file:///Y:/document1/document/RESTAPIDOC.html”	05-Nov-2019 - / Gone through API Documentation for / 1. Generate Keys / 2. Genarate OTP / 3. Forgot password / 4. Change password		In progress	05-Nov-2019 - / Gone through API Documentation for / 1. Generate Keys / 2. Genarate OTP / 3. Forgot password / 4. Change password
16	Self	PK	6. Nov. 2019	Self-Assigned	Explore java code for mobile – backend	06-Nov-2019- / Code exploration in progress. As checked with S.Kri, source code need to be configured from 49 server. Then compile the code using one batch file and then restart node in weblogic server running on 49 server. / This 49 server is being used for development as well as UAT server. Different nodes have been configured for same.		On hold
17	BV	PK	7. Nov. 2019	Shubh-Web-Login-TR	Create a new rest service for “Set new password ” in mobile project.	11-Nov-2019- / Service created and copied in uat environment. / 07-Nov-2019 - / Created the service, but code is not being compiled in local, as per instructions received yesterday(copy the existing bat file and mention the java files need to be compiled) / Roadblock- compillation getting fail due to method not found in some Hex class. Saroj and Rashi may help tomorrow.	1. Define page code / 2. End point will be 0139/set/password/TR / 3. Initially call the public key generation code and then use it to invoke given NEST REST URL. / 4. Send back same response to user as recived from above service	Done		2
18	BV	PK	11. Nov. 2019	Notic-KRA-KUA	migrated to new certificate / Have sit with Dilip and take overview for the certificate updation	14-Nov-2019- / As discussed with Manoj and Dilip, the adhar verification and kyc verification APIs are currently disabled. So code can not be tested. However, as checked with Manoj and Dilip, the code uses certificate from key-value in property file, so there will be no any issue post updating new certificates in UAT. / 13-Nov-2019- / * Certificates have been placed in 172.25.233.26 / * Gaurav Dwivedi has been informed for the same. / * As discussed with Gaurav, he need to confirm if any code change needed for the certificate change? He will call in some time.	The current UIDAI certificate used to encrypt PID block in Authentication request is going to expire by 30th Dec 2019. Please find the below link to the new production public certificate, uidai_auth_prod.cer(Latest), which can be used straight away in authentication request to encrypt the PID block. https://www.uidai.gov.in/916-developer-section/data-and-downloads-section/11349-uidai-certificate-details.html All the ecosystem partners are requested to migrate to the new certificate well before 30th Dec 2019. Transactions using the current certificate post 30th December 2019 may fail, for which UIDAI will not be responsible. Please note that the new certificate is valid until 21st Oct 2022.	Done		1
19	Self	PK	11. Nov. 2019	Self-Assigned	AOP implementation for logging request and response to DB, so that redundant codes should not be written in every requests. / Currently this is being manually written in every requests.			In progress	Code should not be altered, so take precaution before making changes. / Need to know how can we take backup of running code before making changes and also how the backup can be restored, if any issue.	3
20	BV	PK	11. Nov. 2019	Shubh-Web-Login-TR	Change the api url for -Create a new rest service for “Set new password ” in mobile project.			Done	B.V. to share the new url and this we will replace in code	1
21	BV	PK	13. Nov. 2019	Notic-KRA-KUA	Configure code of UIDD code in local eclipse	13-Nov-2019- / * Took codes from Dilip / * Imported codes in local eclipse / * Given property files and keys are not found in any file in given code. Need to get it checked with Dilip. / * As discussed, Dilip has shared KRA project code, hence keys are not being found. Dilip will share correct code tomorrow.		On hold	13-Nov-2019- / * Took codes from Dilip / * Imported codes in local eclipse / * Given property files and keys are not found in any file in given code. Need to get it checked with Dilip. / * As discussed, Dilip has shared KRA project code, hence keys are not being found. Dilip will share correct code tomorrow.	1
22	BV	PK	14. Nov. 2019	Mandatory-Training	Go through courses assigned in https://ivl-eshiksha.com/	Online course. Done.		Done		1
23	BV	PK	14. Nov. 2019	Mandatory-Training	Training in delhi for UIADI on next Saturday.	16-Nov-2019- / Done- Attended the training. It was for anew app lauched by NSDL . Now there will be concept of sub-kua . Sub-KUA will be all broking site. The application will be available for web as well as mobile. It will be released in next 3 months. / 15-Nov-2019- / Scheduled - Received venue details and contact person name. / Scheduled for the training / 14-Nov-2019- / Venue details and contact person has been received. / Need to go on saturday		Done	Date and place will be confirmed by B.V.	2
24	BV	PK	14. Nov. 2019	INET-Request	Raise request to get access on tunnelg.	19-Nov-2019- / Request raised in inet and resolved next day. / 14-Nov-2019- / Raise ticket in inet for tunnelg.		Done	Need to confirm with Dilip for steps to raise request
25	Rsh	PK	15. Nov. 2019	Shubh-Web-Login-TR	Test for “Login post authentication with OTP and set TPIN” APIs as shared from Rashi.	15-Nov-2019- / * APIs mentioned were configured in postman, all steps but the last one is not giving OK result. / * Checking result with Rohit sir for last step.	* 4.22 FORGOT PASSWORD USING OTP / * 4.24 AUTHENTICATION OF OTP / * {04.18 SET MPIN OR REGISTER TPIN DEVICE} / * 4.29 SET TPIN / * 5.1 LOGIN	Done	Debugging for last step mentioned (Login)	2
26	Rsh	PK	15. Nov. 2019	Shubh-Web-Login-TR	Go through documents shared for “Login Process TR”. / Target is to understand steps for login with TPIN.			Done	Go through documents shared for “Login Process TR”. / Target is to understand steps for login with TPIN.	1
27	AKS	PK	19. Nov. 2019	Notic-KRA-KUA	Notis Discontinue -	26-Nov-2019- / After conversation with exchange , some code correction have been done for fetching all data of	Please closed this Requirement by Next Weekend. (discussed Yashpal for the same) … Data need to be send to Yashpal DB as well… and Trade file format need to be made. / Please get the Req closed / 1. Trade file to be import into RTS DB / 2. Trade file download as per NEST Format. / 3. Trade File to be updated in OTS DB for trade/Sales Deshboard. (CM, FNO, CDS)	Done	Target date is next weekend. / Api has been updated and code is running in production from last 10 days. Counts of exhange data is now matching .	1
28	BV	PK	27. Nov. 2019	API-Testing	Test API “Near Real time Notifications - IVL”	27-Nov-2019- / Given api is being successfully called from postman	Test the API Response in Postman and share the result. / REST UAT API URL :- http://172.25.220.124:9080/ibivl/broadcast/message / Json request :- / ------------------- / { / "title": "broad msg test", //Mandatory attribute / "message": "This is test push, Kindly ignore", //Mandatory attribute / "CampaignType": "ivl", //Mandatory attribute / "numberAttbOne": null, / "numberAttbTwo": null, / "stringAttbOne": "", / "stringAttbTwo": "" / } / ----------------------	Done	27-Nov-2019- / Given api is being successfully called from postman	2
29	Self	PK	27. Nov. 2019	Self-Assigned	Spring Boot @Value Exploration			In progress		10
30	Self	PK	27. Nov. 2019	Self-Assigned	Javascript api to create excel like application	27-Nov-2019- / http://embed.plnkr.co/b5EbkTXabBsumaIKA9v4/		Discarded	Not needed	10
31	RaJB	PK	28. Nov. 2019	Notic-KRA-KUA	KRA Code, server(UAT and Production) details gathering	28-Nov-2019- / As discussed with rajeev, the Prod KRA services are hosted on same server, where PAN services are deployed. / Ankit can help for prod server.		Done	Access granted to my id. Analysis and code configuration in local eclipse in progress.	2
32	BV	PK	29. Nov. 2019	Notic-New-Requirement	CM and FO Notise upload timing		----------- / Requirement :- / cm and fo notise upload timing should be start at morning 9:0 am and end at 4:0 pm / cd notise upload timing should be start at morning 9:0 am and end at 5:0 pm	In progress		1
33	BV	PK	29. Nov. 2019	Notic-New-Requirement	Remove property file values hardcoding from Notic code			In progress		1
34	BV	PK	29. Nov. 2019	Notic-Bug-Fix	Getting error “org.hibernate.HibernateException: The internal connection pool has reached its maximum size and no connection is currently available”	29-Nov-2019- / Log file obtained from Anmol from production. Working to identify issue.		Done	Issue was with connection pooling. Issue addressed and rectified.	1
35	BV	PK	29. Nov. 2019	Notic-KRA-KUA	Send data for classes used in CM and FO trades fetch			Done	Data sent over mail	1
36	BV	PK	13. Dec. 2019	Notic-Bug-Fix	Getting Error / “com.google.gson.JsonSyntaxException: java.lang.IllegalStateException: Expected BEGIN_OBJECT but was STRING at line 1 column 1 path $”	13-Dec-2019- / The issue is occuring while parsing the JSON response received from Exchange server. Added code to log response in files under seq folder.		Done	Issue was with data coming from exchange. Now issue is not reporodcing.	1
37	BV	PK	23. Dec. 2019	Shubh-Web-Login-TR	Create a new rest service for / “select t.flag from vw_branch_non_branch_client t / where t.ref_Id = '27374';”	23-Dec-2019 / Service created and details shared with Rashi, Saroj and Brijesh		Done	Details sent over mail	1
38	BV	PK	24. Dec. 2019	Shubh-Web-Login-TR	Fetch NSE IPO List from given API and get it saved in DB as well as put it in cache for further quick use	26-Dec-2019 / API Created and added in StartupServlet.		Done	26-Dec-2019 / API Created and added in StartupServlet.	1
39	BV	PK	27. Dec. 2019	Shubh-Web-Login-TR	Use the below procedure for validation of Individual DP account no will be allowed to place IPO bid. / This procedure return flag and messages / If pv_flag = ‘S’ then allowed / If pv_flag = ‘F’ then show the DB messages. / PKG_IPO.DP_TYPE_VALIDATION(pv_dp_acc_no VARCHAR2, / pv_flag out VARCHAR2, / pv_msg out VARCHAR2)	27-Dec-2019 / API Created and code added in dev environment. Informed Brijesh sir for same.		Done	27-Dec-2019 / API Created and code added in dev environment. Informed Brijesh sir for same.	1
40	Self	PK	15. Dec. 2019	KRA-SFTP-CODE-Configuration	Configure code of KRA and SFTP in local machine and put the code in gitlab server	06-Jan-2020 / Code uploaded in GitLab. / 30-Dec-2019 / Analysis and copy/configuration of (KRA/SFTP) code into local eclipse is in progress. / 27-Dec-2019 / Access to UAT and Prod servers has been granted through PAM /ARCON. / 18-Dec-2019 / Access to UAT and prod server has been requested in tool.		Done	Access granted to my id. Analysis and code configuration in local eclipse in progress.	2
41	BV	PK	31. Dec. 2019	Shubh-Web-Login-TR	Create a new rest service for “"/0142/nse/ipo/master"”			Done	http://172.25.219.49:81/mpib/v2/0142/nse/ipo/master	1
42	BV	PK	2. Jan. 2020	Shubh-Web-Login-TR	Update in rest service for “"/0142/nse/ipo/master"” / Also return tickSize			Done	http://172.25.219.49:81/mpib/v2/0142/nse/ipo/master	1
43	BV	PK	2. Jan. 2020	Shubh-Web-Login-TR	Create method to get login data from given table and call login API and write response and token in database and application object respectively	03-Jan-2020 / Code added. / Updated below files / com/indiabulls/trade/order/FetchChildRec.java / com/indiabulls/mpib/v2/nse/ipo/NSEApiRequest.java / servlet/StartupServlet.java / com/indiabulls/mpib/v2/nse/ipo/NseIPOBo.java		Done	Need to call the method on application start up and store token object in session object.	1
44	BV	PK	6. Jan. 2020	Shubh-Web-Login-TR	Update in rest service for “"/0142/nse/ipo/master"” / Also return cutOffPrice			Done		1
45	BV	PK	7. Jan. 2020	Notic-Bug-Fix	Utility should run on dates when market is open. Else skip run for utility for that day.			In progress	Brijesh sir will share the table details for information for market open for a day.	2
46	BV	PK	8. Jan. 2020	KRA-Issue	DOB Validation is not happening now. Earlier it was working.	09-Jan-2020- / As checked the cvlkra api do not need DOB data as input. So this is not included in DOB validation.		Done		2
47	AKS	PK	9. Jan. 2020	KRA-Documentation	Share cvlkra api documentation request and response used in KRA application			In progress		1
48	AKS	PK	9. Jan. 2020	SFTP-Documentation	Share SFTP application documentation request and response used in KRA application			In progress		1
49	Self	PK	14. Jan. 2020	Self-Assigned	Read for IPO in share market, from google, zerodha.			In progress		1
50	BV	PK	14. Jan. 2020	NSE-IPO-API-CREATION	Read NSE IPO API document			Done	Page no-37	1
51	BV	PK	20. Jan. 2020	SFTP-Issue-Replication	Documents for 515 clients still pending.			Discarded	SFTP Server is not accesible from KRA Prod server. / Ankit is following up for the re-establishment of connection.	1
52	BV	PK	20. Jan. 2020	Candidate-Screening	Shortlist candidates for the drive on coming saturday			Done	Updated document shared to Brijesh sir.	1
53	AKS	PK	21. Jan. 2020	Notic-Protocol-update	Read PROTOCOL DOCUMENTS for Notis Application for updated protocols and change I code,if needed, accordingly.			Done	Now only 34 in stead of 40 fields will come for cm trade response. / No change for CD and FO responses. / Will raise another task to update in code for CM	1
54	AKS	PK	21. Jan. 2020	SFTP-Documentation	SFTP Process diagram			Done	SFTP Document shared	1
55	BV	PK	23. Jan. 2020	Notic-Protocol-update	Update in Notis code for CM response / Now only 34 in stead of 40 fields will come for cm trade response. / Need to update CM response code accordingly			Testing	Coding done. Now the target tables to be updated as currently data going in dummy tables. / Target tables to be updated as real tables.	1
56	BV	PK	23. Jan. 2020	NSE-IPO-API-CREATION	Add “Authorization” token for Callback requests. / As discussed with Ajay sir and Brijesh sir, encoded authorization token string which is supplied in Callback request will be matched, post decode, with the string stored in DB. / Also this API should be host on server which is publicly accesible, hence it might be moved from Mobile API server to ShubhWeb server.			Done
57	self	PK	23. Jan. 2020	Self-Assigned	Obtain rent-agreement / Prepare rent reciepts / Get Online bank statements for rent			Discarded
58	AKS	PK	24. Jan. 2020	Self-Assigned	Like Omnesys API Documentation, create API documentation for ShubhWeb.			Discarded		2
59	DJ	PK	19. Feb. 2020	Shubh-Web-Vulnerability Fix	fix the vulnerabilities reported in shubhweb.indiabulls.com			Discarded
60	AKS	PK	26. Feb. 2020	Notic-New-Requirement	Change the target tables in stored procedures and make live post testing			On hold	16-Mar-2020-Brajesh sir need to do changes in procedure / Stop existing flow / Initially only CD will be tested.
61	AKS	PK	26. Feb. 2020	Notic-New-Requirement	Make documentation for Notis API (Existing flow and new flow for OTS and RMS)			On hold
62	BV	PK	26. Feb. 2020	Shubh-Web-API	API for tradeHistory is giving lesser rows , however in simulator all rows are returning (Client specific issue)			Discarded	Hopefully issue got resolved
63	BV	PK	26. Feb. 2020	Notic-New-Requirement	Create API for RMS Team for FO and CD			On hold	API is ready
64	BV	PK	26. Feb. 2020	Shubh-Web-API	Merge Shubh web code on UAT branch and Prod tag			Done
65	AKS	PK	12. Mar. 2020	Shubh-Web-API	Phonepe merchant id changed, need to do according changes			In progress	Two rows are being generated, one for I and one for C. merchant ref no of I row is not able to be searched on PhonePe API
66	DJ	PK	16. Mar. 2020	Shubh-Web-API	VA-PT issue closure-Shubh web	Earlier task was being worked by Aditya. Now Shruti is taking care of this.		In progress	Need to get current status for the tasks . Check if any help/query.
67	DJ	PK	16. Mar. 2020	PowerIndiaBulls Site	VA-PT issue closure- Power Indiabulls site	Shruti is taking care of this		In progress	Need to get current status for the tasks . Check if any help/query.
68	AKS	PK	12. Mar. 2020	Shubh-Web-API	Changes on Payment Gateway page			Analysis	Change Need to be done in mobile as well as web
69	AKS	PK	12. Mar. 2020	Shubh-Web-API	Portfolio- Fy activity / Plan for generating the Portfolio report for fy 19-20 so the business can send the same to clients as last fy 18 - 19			Analysis
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687

## Acronym
Users
Brijesh Vaishya	BV
Premendra Kumar	PK
Self	Self
Ajay Singh	AKS
Deepak Jain	DJ
Rajeev Jha/Brijesh	RaJB
Rashi Shrivastava	Rsh

## GITvsSVN
Feature	GIT	SVN
Server Architecture	Git software is installed on a workstation and acts as a client and a server. Every developer has a local copy of the full version history of the project on their individual machine. Git changes happen locally. So, the developer doesn’t have to be connected all the time. Once all the files are downloaded to the developer’s workstation, local operations are faster.	SVN has a separate server and client. Only the files a developer is working on are kept on the local machine, and the developer must be online, working with the server. Users check out files and commit changes back to the server.
Branching and Merging	Git branches are only references to a certain commit. They are lightweight — yet powerful. You can create, delete, and change a branch at any time, without affecting the commits. / If you need to test out a new feature or you find a bug, you can make a branch, make the changes, push the commit to the central repo, and then delete the branch.	SVN branches are created as directories inside a repository. This directory structure is the core pain point with SVN branching. When the branch is ready, you commit back to the trunk. / Of course, you’re not the only one merging changes. Your version of the trunk might not reflect developers’ branches. This means conflicts, missing files, and jumbled changes riddle your branch. / This makes for a complicated branching and merging model. This is also time-consuming to manage.
Usability	Git also uses the command line as the primary user interface. But the syntax in Git can overwhelm beginners.	SVN uses the command line as the primary user interface. It is more readily used by non-programmers who want to version non-code assets.

## Values
Task Group
Self-Assigned
Code-Review-Release-Mgmt
Shubh-Web-BOR-Jar
Notic-KRA-KUA
Shubh-Web-Login-TR
Mandatory-Training
INET-Request
API-Testing
Notic-New-Requirement
Notic-Bug-Fix
KRA-SFTP-CODE-Configuration
KRA-Issue
KRA-Documentation
SFTP-Documentation
NSE-IPO-API-CREATION
SFTP-Issue-Replication
Candidate-Screening
Notic-Protocol-update
Shubh-Web-Vulnerability Fix
Shubh-Web-API
PowerIndiaBulls Site
Notis-RMS-Changes

## Scheduled
Task	Description	Frequency	Last done on
Take Bookmark from Chrome		Twice in week( Wednesday Friday)	Nov 27, 2019
Copy Tasks.ods file to 149 server		Twice in week( Wednesday Friday)
Take notepad++ session backup		Twice in week( Wednesday Friday)	Nov 11, 2019